## Sheet1
|  |  | Requirements | Arbeittag | KW - 16 (14. April - 20. April) | [6 empty] | KW - 17 (21. April - 27. April) | [6 empty] | KW - 18 (28. April - 04. Mai) | [6 empty] | KW - 19 (05. Mai - 11. Mai) | [6 empty] | KW - 20 (12. Mai - 18. Mai) | [6 empty] | KW - 21 (19. Mai - 25. Mai) | [6 empty] | KW - 22 (26. Mai - 01. Juni) | [6 empty] | KW - 23 (02. Juni - 08. Juni) | [6 empty] | KW - 24 (09. Juni - 15. Juni) | [6 empty] | KW - 25 (16. Juni - 22. Juni) | [6 empty] | KW - 26 (23. Juni - 29. Juni) | [6 empty] | KW - 27 (30. Juni - 06. July) | [6 empty] | KW - 28 (07. July - 13. July) | [6 empty] | KW - 29 (14. July - 20. July) | [6 empty] | KW - 30 (21. July - 27. July) | [6 empty] | KW - 31 (28. July - 03. August) | [6 empty] | KW - 32 (04. August - 10. August) | [6 empty] | KW - 33 (11. August - 17. August)
[5 empty] | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So
Introduction |  |  |  | 1 | KW - 16 (14. April - 20. April) Mi: 100%; KW - 20 (12. Mai - 18. Mai) Mi: Concept Pre; KW - 24 (09. Juni - 15. Juni) Mi: Design Pre; KW - 25 (16. Juni - 22. Juni) Di: Excursion ATB; KW - 29 (14. July - 20. July) Mi: Final Pre; KW - 33 (11. August - 17. August) Mi: Final report submission
Group Definition |  |  |  | 1 | KW - 17 (21. April - 27. April) Mi: 100%
Planning |  |  |  | 10 | KW - 18 (28. April - 04. Mai) Mo: 90%
Time Definition |  |  |  | 7 | KW - 19 (05. Mai - 11. Mai) Mi: 10%; KW - 20 (12. Mai - 18. Mai) Mi: Concept Pre
Concept Presentation |  |  |  | 1 | bar: KW - 20 (12. Mai - 18. Mai) Mi
Basic Configuration |  |  |  | 21 | bar: KW - 20 (12. Mai - 18. Mai) Mi
| Initialisation of project |  |  | 6 | bar: KW - 20 (12. Mai - 18. Mai) Mi
Configuration of Development environment and Version
Configure Docker and Docker Compose
Record the project structure and requirments documents
| Configure Basic Applications |  |  | 6 | bar: KW - 21 (19. Mai - 25. Mai) Di
Implement Docker containers for Label Studio and YOLO services
Configure shared volumes for data exchange
Set up network communication
| YOLO Service Implementation |  |  | 6 | bar: KW - 21 (19. Mai - 25. Mai) So
Integrate the YOLO_v8 model
Implement the prediction functionality
Set up the model training environment
Develop a data processing pipeline
| Label Studio Integration |  |  | 6 | bar: KW - 22 (26. Mai - 01. Juni) Fr
Configure the Label Studio project
Implement API communication
Create annotation templates
Test the basic workflow
Core Functionality Development |  |  |  | 21 | bar: KW - 23 (02. Juni - 08. Juni) Do
| Active Learning Loop Implementation |  |  | 6 | bar: KW - 23 (02. Juni - 08. Juni) Do
Develop image prediction processing logic
Implement pre-annotation upload to Label Studio
Create a task monitoring mechanism
|  | Establish a prediction - annotation - training loop |  |  | KW - 24 (09. Juni - 15. Juni) Mi: Design Pre
Design Presentation |  |  |  | 1 | bar: KW - 24 (09. Juni - 15. Juni) Mi
| Data Conversion Functionality |  |  | 6 | bar: KW - 24 (09. Juni - 15. Juni) Mi
Develop conversion between YOLO format and Label Studio format
Establish a data standardization process
Handle multiple image formats
| Model Training Optimization |  |  | 6 | bar: KW - 25 (16. Juni - 22. Juni) Mo
Implement incremental training logic
Optimize dataset generation
Develop model version management
Configure training parameter tuning
| System Integration and Testing |  |  | 5 | bar: KW - 25 (16. Juni - 22. Juni) Sa
Integrate all components
Conduct end-to-end testing
Fix communication issues
Optimize the workflow
Function Expansion and Optimization |  |  |  | 21 | bar: KW - 26 (23. Juni - 29. Juni) Do
| Annotation Quality Improvement |  |  | 6 | bar: KW - 26 (23. Juni - 29. Juni) Do
Implement uncertainty sampling strategy
Add confidence threshold adjustment
Develop annotation quality evaluation metrics
Implement hard example prioritization strategy
| User Experience Improvement |  |  | 6 | bar: KW - 27 (30. Juni - 06. July) Di
Add progress visualization
Improve the logging system
Develop a simple monitoring interface
Add system status notifications
| Performance Optimization |  |  | 6 | bar: KW - 27 (30. Juni - 06. July) So
Optimize prediction speed
Improve batch processing efficiency
Implement resource usage control
| Advanced Feature Implementation |  |  | 6 | bar: KW - 28 (07. July - 13. July) Fr
Add multi-model support
Develop custom label mapping
Implement more complex preprocessing options
|  | Add advanced training configurations |  |  | KW - 29 (14. July - 20. July) Mi: Final Pre
Design Presentation |  |  |  | 1 | bar: KW - 29 (14. July - 20. July) Mi
System Stability and Scalability |  |  |  | 20 | bar: KW - 29 (14. July - 20. July) Do
| Error Handling and Recovery |  |  | 6 | bar: KW - 29 (14. July - 20. July) Do
Implement robust error handling
Add automatic recovery mechanisms
Develop system status checks
Implement data backup functionality
| Security Enhancement |  |  | 6 | bar: KW - 30 (21. July - 27. July) Di
Strengthen API security
Implement authentication
Add log auditing
Configure storage encryption
| Scalability Improvement |  |  | 6 | bar: KW - 30 (21. July - 27. July) So
Optimize container configuration
Implement more flexible deployment options
Add resource scaling capabilities
Develop support for distributed processing
| Documentation and Testing |  |  | 6 | bar: KW - 31 (28. July - 03. August) Do to KW - 32 (04. August - 10. August) Di
Complete system documentation
Write user guides
Create tutorials and examples
Conduct comprehensive system testing
Release Preparation and Deployment |  |  |  | 9 | bar: KW - 32 (04. August - 10. August) Di to KW - 33 (11. August - 17. August) Mi
| Integration Testing |  |  | 5 | bar: KW - 32 (04. August - 10. August) Di to KW - 32 (04. August - 10. August) Sa
Check long-term stability
Perform multi-user scenario testing
| Bug Fixing and Optimization |  |  | 5 | bar: KW - 32 (04. August - 10. August) Sa to KW - 33 (11. August - 17. August) Mi
Resolve known issues
Optimize system performance
Improve edge case handling
Conduct final code review
Final report submission |  |  |  | 1 | bar: KW - 33 (11. August - 17. August) Mi
Project Closure |  |  |  | 115 | KW - 16 (14. April - 20. April) Mo: 15.8%
Congratulations